## Estimation_V1
Features | Optimistic | Pessimistic | Most Likely
Analysis | 8 | 12 | 10
UI Design | 32 | 40 | 36
FRONTEND DEVELOPMENT (NextJS) |  |  |  | Summary | PERT
1. Project Setup & Environment - Next.js setup, folder structure, routing, base components, environment variables | 8 | 12 | 10 | Development + Design | 251
2. Landing Page Templates (6–8) - Creation of 6–8 responsive templates with dynamic content areas (Hero, USPs, testimonials, CTA) | 24 | 36 | 32 | QA | 50.2
3. Lead Capture Form - Form UI with inline validation, package auto-tagging, error states, responsive handling | 12 | 16 | 14 | PM Effort | 25.1
4. Thank You Page - Page with success message & conversion tracking code integration | 4 | 8 | 6 | Contingency [official travel expenses/unfortunate change in the projects/purchasing H/W or S/W] | 12.55
5. SEO Implementation - Meta tags, alt texts, schema markup, performance optimization | 6 | 8 | 6 | UAT | 20.08
6. Analytics & Tracking - GTM/pixel integration, form submission event triggers | 4 | 8 | 6
7. Campaign Routing - Dynamic routing for 6–8 packages, SEO-friendly URLs | 8 | 12 | 10 | Total | 358.93
BACKEND CMS (Strapi/Admin)
1. CMS Setup & Configuration - Drupal/Strapi setup, content types for landing pages & Thank You page | 8 | 12 | 10
2. Template Management - Backend structure for 6–8 templates, metadata fields, scheduling | 20 | 32 | 28
3. Lead Capture API - API creation to send leads to CRM with package tagging | 8 | 16 | 12
4. Form Field Management - CMS-based configurable fields for forms (if required) | 4 | 8 | 6
5. Thank You Page CMS Control - Content management & conversion pixel configuration | 4 | 8 | 6
6. SEO Metadata Management - CMS fields for meta tags, schema, Open Graph | 4 | 8 | 6
7. Campaign Scheduling - Backend functionality to activate/deactivate landing pages | 8 | 12 | 10
ADMIN PANEL SETUP (Strapi Admin)
Admin Setup | 6 | 10 | 8
Template Management in the Admin Panel | 8 | 12 | 10
Form data capture in the Admin Panel | 4 | 8 | 6
Content Entry | 16 | 24 | 20
| 196 | 302 | 252