## Mobile APP Breakdown
Features | Optimistic | Pessimistic | Most Likely
Frontend
Project configuration | 8 | 12 | 10 | Summary | PERT
Employee login , Authentication via OTP , device validation | 8 | 12 | 10
Employee registration | 4 | 8 | 6
Login with biometric (Face id,fingerprint) | 8 | 12 | 10 | Development + Design | 712.5 | 819.375
Employee Profile & Dashboard Basic info, department, contact, manager name, notification settings | 16 | 20 | 18 | QA + Security Check
Grievance Redressal System Category-wise complaints, file uploads, tracking, escalation mechanism | 30 | 34 | 32 | DevOps
Employee Feedback & Survey Anonymous & named feedback, MCQ, text inputs, 1–5 star rating | 20 | 24 | 22 | PM Effort
Training Materials PDF repository + Training Calendar | 20 | 24 | 22
Recognition & Rewards Award templates, nomination process,post award, comments, likes | 32 | 40 | 36 | UAT
Communication Module Comet chat real time chatting, 1:1 and group chat | 20 | 24 | 22 | Total | 713
company-wide announcements with filters , Group Discussions | 16 | 20 | 18
Incident Reporting Location, urgency tagging, file uploads, escalation to managers/admins | 24 | 28 | 26 | Support [2 months]
Compliance Docs PDFs for safety/regulatory policies to be browsed by employees | 16 | 18 | 20 | Grand Total | 713
Innovation/Idea Box Tab for employees to submit suggestions or ideas (non-anonymous) | 12 | 16 | 14
Search Functionality Global search across announcements, documents, events, etc. | 20 | 24 | 22 | Digital Magazine
Notifications , filter , firebase Push + SMS/email-based alerts at every stage across modules | 24 | 28 | 26
Dark & light mode | 32 | 40 | 36
Design implementation in mobile app | 80 | 100 | 90
Multi-lingual Support (English,Hindi) | 20 | 27 | 18
Backend
Employee login , Authentication via OTP , device validation | 16 | 20 | 18
Login with biometric (Face id,fingerprint) | 8 | 12 | 10
Employee Profile & Dashboard Basic info, department, contact, manager name, notification settings | 12 | 16 | 14
Grievance Redressal System Category-wise complaints, file uploads, tracking, escalation mechanism | 24 | 40 | 32
Employee Feedback & Survey Anonymous & named feedback, MCQ, text inputs, 1–5 star rating | 12 | 16 | 14
Training Materials PDF repository + Training Calendar | 16 | 24 | 20
Recognition & Rewards Award templates, nomination process,post award, comments, likes | 24 | 40 | 32
company-wide announcements with filters , Group Discussions | 16 | 20 | 18
Incident Reporting Location, urgency tagging, file uploads, escalation to managers/admins | 12 | 18 | 16
Search Functionality Global search across announcements, documents, events, etc. | 16 | 24 | 20
Notifications , filter , firebase Push + SMS/email-based alerts at every stage across modules | 32 | 48 | 40
Multi-lingual Support (English,Hindi) | 16 | 24 | 20
TOTAL | 614 | 813 | 712