## Web APP Breakdown (Admin)
Sample
Features | Optimistic | Pessimistic | Most Likely
Frontend |  |  |  | Summary | PERT
User Management (Includes login and forgot password) | 16 | 20 | 18
Testimonial Management | 8 | 12 | 10 | Development + Design | 273 | 313.95
Feedback and Report Management | 12 | 18 | 16 | QA + Security Check | 54.6
Escalation Management | 8 | 12 | 10 | DevOps | 13.65
Announcement Management | 8 | 12 | 10 | PM Effort | 40.95
Awards & Recognition Management along with template | 12 | 16 | 14 | Contingency [official travel expenses/unfortunate change in the projects/purchasing H/W or S/W] | 21.84
Notification Management | 2 | 6 | 4 | UAT | 27.3
Training Management (Includes video and pdf) | 12 | 16 | 14 | Total | 431
Role Management (Role based access control included) | 16 | 24 | 20 | Support [2 months]
Multi-lingual support (English and Hindi) | 16 | 24 | 20 | Grand Total | 431
Settings | 4 | 8 | 6
Backend
User Management (Includes login and forgot password) | 12 | 16 | 14
Testimonial Management | 8 | 12 | 10
Feedback and Report Management | 10 | 14 | 12
Escalation Management | 8 | 14 | 12
Announcement Management | 8 | 14 | 12
Awards & Recognition Management along with template | 12 | 16 | 14
Notification Management | 2 | 6 | 4
Training Management (Includes video and pdf) | 8 | 12 | 10
Role Management (Role based access control included) | 24 | 32 | 28
Multi-lingual support (English and Hindi) | 8 | 12 | 10
Setttings | 4 | 8 | 6
TOTAL | 218 | 324 | 274