## Estimation Breakdown - DrupalS
Sample
Area | Feature / Task Description | Optimistic (hrs) | Pessimistic (hrs) | Most Likely (hrs)
Analysis |  | 40 | 80 | 64
UI Screen Design |  | 80 | 120 | 100
FRONTEND (NextJS) |  |  |  |  | Summary | PERT
Homepage UI | Responsive homepage layout, hero banner, news, vessel search bar | 16 | 28 | 24 | Development + Design | 816.5
Vessel List Page | Vessel listing (~70K records), pagination, filters, responsive grid | 20 | 36 | 28 | QA + Security Check | 163.3
Vessel Detail Page (Overview) | Full vessel overview page with 10+ attributes, layout, and image | 20 | 36 | 28 | DevOps | 40.825
Vessel Search & Filters | Multi-parameter search (name, IMO, flag, type, operator) + autocomplete | 22 | 40 | 32 | PM Effort | 122.475
News Listing & Details | Integration of Drupal news content with detail view | 12 | 20 | 16 | Contingency [official travel expenses/unfortunate change in the projects/purchasing H/W or S/W] | 65.32
Magazines Listing & Details | Magazine archive list, preview/download page | 12 | 20 | 16 | UAT | 81.65
About Us / Contact Pages | Static pages, responsive content, contact form validation | 12 | 20 | 16 | Total | 1290
Other Inner Pages | Other informative Static informative pages like FRP, Regulations, Privacy Policy, DMCA pages | 12 | 20 | 16
Share Functionality | Share in Social Media (Native) | 12 | 20 | 16 | Grand Total | 1290
Form Pages | Form and Query Pages - Advertise with Us, Write with Us, Comment Sections etc | 16 | 28 | 24
Global Navigation | Header, footer, menus, breadcrumbs, responsive nav | 16 | 28 | 24
API Error/Fallback UI | Display message for data unavailability | 12 | 20 | 16 | Total Timeline | 12-14 Working Weeks
SEO & Analytics Integration | Structured metadata, schema, Google Analytics setup | 8 | 12 | 10
Performance Optimization | Lazy loading, caching, image optimization | 16 | 28 | 24
BACKEND (Drupal/Node)
Drupal Setup | Environment configuration, module installation | 8 | 12 | 10
Content Types – News & Magazine | Field setup, taxonomy, view templates | 12 | 20 | 16
Other Inner Pages | Other informative Static informative pages like FRP, Regulations, Privacy Policy, DMCA pages | 12 | 20 | 16
Form Pages | Form and Query Pages - Advertise with Us, Write with Us, Comment Sections etc | 16 | 28 | 24
Content Type – Vessel | Create CT with 10+ attributes (IMO key, relationships) | 16 | 28 | 24
Vessel API Integration | Connect external API, daily cron sync job | 16 | 28 | 24
API Error Handling & Logs | Sync failure logs, error notifications | 12 | 20 | 16
Data Normalization & Variation Handling | Handle field inconsistencies, updates | 12 | 20 | 16
REST API Exposure | Custom endpoints for NextJS consumption | 10 | 16 | 14
Search API Enhancements | Enable multi-parameter queries for search | 10 | 16 | 14
GDPR & Policy Pages | Privacy policy, disclaimer setup | 5 | 8 | 6
ADMIN (Drupal /Strapi CMS)
User Roles & Permissions | Define admin, editor roles | 8 | 12 | 10 | 816.5
Admin Dashboard (API Logs) | Display sync success/failure reports | 12 | 20 | 16
Vessel Management | Create/Edit vessel data manually in admin | 12 | 20 | 16
Vessel Image Management | Upload and manage vessel images (linked to IMO) | 10 | 16 | 14
News & Magazine CRUD | Add/edit content, media upload | 10 | 16 | 14
Basic Page Setup | Basic Home Page Content Block setup | 8 | 12 | 10
Informative Inner Page Setup | Paragraph Module setup and Content Block creation | 8 | 12 | 10
Content Type, Taxonomy Block | Content Type and Taxonomy Block Setip | 8 | 12 | 10
Global Settings & Menu Mgmt | Navigation menus, SEO meta, footer links | 8 | 12 | 10
| Total | 539 | 904 | 744
| TOTAL | 942 | 1580 | 1300